## Procurement Plan
IMPLEMENTER (OWNER) | IMPLEMENTATION LOCATION | WORKPLAN ACTIVITY REFERENCE | DESCRIPTION OF PROCUREMENT ACTIVITIES | BUDGET REFERENCE NUMBER | APPROVED BUDGET AMOUNT (NGN) | APPROVED BUDGET AMOUNT (USD) | PPM | NON-PPM | FY25 TARGETS | QUANTITY | UOM | RESPONSIBLE PR STAFF | MODE OF PROCUREMENT | PROCUREMENT COMMITTEE REVIEW | APPLICABLE SOLICITATION METHOD | PROCUREMENT START DATE | PROCUREMENT METHOD | START DATE OF RFQ | CLOSING DATE OF RFQ | EVALUATION DATE | NEGOTIATION | DATE CBA AND REPORT IS FINALISED | DATE PURCHASE ORDER/PC IS ISSUED | SELECTED SUPPLIER | EXPECTED DELIVERY DUE DATE | DELIVERY LEADTIME | DELIVERY TO | PROCUREMENT PERFORMANCE/MONITORING REMARKS | PROCUREMENT PERFORMANCE SCORE
Project Manager A | Lagos Office | WP-001 | Office Supplies and Equipment | BUD-2025-001 | 500,000 | 1,200 | Yes | No | Q1 2025 | 50 | Units | John Doe | Open Tender | Required | RFQ | 2025-01-15 | Competitive Bidding | 2025-01-20 | 2025-01-30 | 2025-02-05 | 2025-02-10 | 2025-02-15 | 2025-02-20 | ABC Suppliers Ltd | 2025-03-01 | 10 days | Lagos Office | On track - procurement proceeding as planned | 85
Project Manager B | Abuja Office | WP-002 | IT Equipment Procurement | BUD-2025-002 | 2,000,000 | 4,800 | No | Yes | Q2 2025 | 20 | Units | Jane Smith | Restricted Tender | Required | RFP | 2025-02-01 | Competitive Bidding | 2025-02-10 | 2025-02-28 | 2025-03-05 | 2025-03-12 | 2025-03-20 | 2025-03-25 | TechCorp Solutions | 2025-04-15 | 21 days | Abuja Office | Pending vendor selection | 70